# Demo Seed — 'Pad B Schedule Conflict' Email Thread (12 messages)

INSTRUCTOR USE: seed these into the demo mailbox as a thread the morning of delivery. Synthetic content.

## Message 1 — From: M. Reyes (Program)

Team - heads up, Meridian wet dress moved to 21 July. Does this collide with the Pad B maintenance window?

## Message 2 — From: J. Okafor (GSE)

Yes - Pad B deluge system inspection is booked 20-22 July. We can't run wet dress during inspection.

## Message 3 — From: T. Nguyen (Ops)

Could we compress the inspection to 20-21? Vendor said two days minimum last time we asked.

## Message 4 — From: D. Park (Facilities)

Vendor quote allows a one-day compression for +$4,200 expedite. Need approval by the 14th.

## Message 5 — From: M. Reyes (Program)

What's the impact if wet dress slips to the 22nd instead?

## Message 6 — From: T. Nguyen (Ops)

LRR is the 24th - a 22 Jul wet dress leaves one contingency day. Tight but workable.

## Message 7 — From: J. Okafor (GSE)

Reminder: chilldown valve retest must precede wet dress. Spares arrive the 15th, retest the 17th.

## Message 8 — From: D. Park (Facilities)

Also - who owns the updated range booking if dates move? That has to be refiled 72h ahead.

## Message 9 — From: M. Reyes (Program)

Good question. Last time ops filed it, but program signed. Let's settle this.

## Message 10 — From: T. Nguyen (Ops)

Static fire window on the range calendar still shows the OLD date. Someone needs to correct it.

## Message 11 — From: D. Park (Facilities)

Escalating: fire marshal inspection for the VIP area is also 21 Jul. Three things on one day now.

## Message 12 — From: M. Reyes (Program)

OK - decision needed: expedite inspection ($4.2K), slip wet dress to the 22nd, or move the fire marshal. Opinions by EOD Thursday please.

Buried action items (answer key): expedite approval by 14 Jul ($4,200, owner Facilities/D. Park pending program approval); valve retest 17 Jul (Okafor); range booking re-file owner UNSETTLED; range calendar static-fire date correction UNOWNED; fire marshal conflict 21 Jul (Park).