# Skyward Dynamics kickoff — raw notes (7 Jul)

attendees: reyes, nguyen, park, +3 skyward (chen - PM, watts - safety, ito - integration)

skyward wants first launch in the 28 jul window?? aggressive. chen says vehicle ships on the 12th

- integration bay 2 available from 14th - park to confirm crane cert current

insurance cert STILL not received - 45 day clock?? someone check the math vs first window - who owns chasing this??

watts asked for range safety policy rev 7 - nguyen sending today

weekly integration mtgs start next tues - ito wants them 0900, reyes prefers 1400 - unresolved

range fee invoice - chen thought it was 150k?? actual is 180k per agreement - reyes to send clause + invoice schedule

ACTION chen sending integrated master schedule by friday

cat-3 certs: skyward pad crew of 6, only 2 certified. recert class 10 jul has 3 seats left. watts to enroll 3, remaining 1 next month??

park - VIP viewing area question came up again, defer to campaign team

parking + badging for skyward staff - 8 people, V badges initially, escort rules CHANGED in rev 7 - make sure they know 1:1 now

next sync: thursday after standup