# Launch Campaign Status Report — Orbital Lift LV-2 'Meridian' — Week 28

SYNTHETIC TRAINING DOCUMENT. Prepared by: Program Office. Distribution: internal.

# 1. Campaign Summary

The Meridian campaign remains on track for a launch window opening 28 July 2026. Vehicle integration is 82% complete. Static fire completed 30 June with one anomaly (GSE chilldown valve V-114) since resolved. Range booking for the primary window is confirmed; backup window (4-6 August) booking is pending tenant signature.

# 2. Schedule

Vehicle integration complete — 16 July (forecast, 2 days late vs baseline)

Wet dress rehearsal — 21 July

Launch readiness review — 24 July

Window opens — 28 July 0600-1000 local

# 3. Risk Register (Top 5)

| Risk ID | Description | Owner | Status |
| --- | --- | --- | --- |
| R-081 | Chilldown valve spares lead time exceeds 3 weeks | J. Okafor (GSE) | Mitigating — spares ordered 1 Jul |
| R-104 | Backup window range booking unsigned | M. Reyes (Program) | OPEN — signature needed by 11 Jul |
| R-117 | Cat-3 certification lapses for 4 pad crew before window | T. Nguyen (Ops) | Mitigating — recert class 10 Jul |
| R-092 | Weather: seasonal afternoon storms vs 0600 window | Meteorology | Accepted — morning window chosen |
| R-121 | Tenant insurance certificate not yet on file | UNASSIGNED | OPEN |

# 4. Budget

Campaign spend is $4.31M against a $4.6M budget (93.7%). Overtime driven by the static-fire anomaly accounts for $61K of variance. No further variance expected if the primary window holds.

# 5. Decisions Needed This Week

Approve backup-window booking signature (owner: Program, due 11 Jul)

Approve weekend recertification class funding ($8.5K)

Confirm VIP viewing area capacity (fire marshal limit 120)